## Sheet1
| 2023 | [7 empty] | 2024
Task | week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12 | week13 | week14 | week15 | week16 | week17 | week18 | week19 | week20
|  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
Background Research | bar: 2023 week1 to 2023 week2
Data Collection & Analysis | bar: 2023 week2 to 2023 week4
Create User Interfaces | bar: 2023 week4 to 2023 week7
Front-End design | bar: 2023 week7 to 2024 week13
Back-End Development | bar: 2024 week11 to 2024 week16
Testing | bar: 2024 week16 to 2024 week18
Finalizing the Project | bar: 2024 week18 to 2024 week19
|  | backgroud4 |  | 2
|  | dataCollec2 |  | 2
ui2
FE 3
BE 5
finalizing 3
testing 2